## Sheet1
Data Visualization Project - Project plan - US Companies Exploration App
Project Team members : Luis Davalos, Krunal Panchal, Brown Varghese, Radha Mahalingam
Porject Tasks
| Sno. | Activity Name | Owner | Team assisting | Duration | Start | End | Status | Comments
| 1 | Create Slack Channel | Radha |  |  | 2019-05-04 | 2019-05-04 | Complete
| 2 | Create Github Repository | Brown |  |  | 2019-05-04 | 2019-05-04 | Complete
| 3 | Project Idea Finalization | Luis, Brown, Krunal, Radha |  |  | 2019-05-04 | 2019-05-04 | Complete
|  | Data Sources | Radha, Luis, Krunal |  |  | 2019-05-04 | 2019-05-04 | Complete | From Kaggle, Nasdaq Website
| 4 | Project Requirement Definition | Radha | Luis, Krunal, Brown |  | 2019-05-04 | 2019-05-06 | Complete
| 5 | Technical specification | Radha | Luis, Krunal, Brown |  | 2019-05-06 | 2019-05-08 | In Progress
|  | Extract, consolidate & generate CSV file | Krunal | Brown, Luis, Radha |  | 2019-05-06 | 2019-05-06 | Not Started
|  | Clean & Transform Data | Brown | Krunal, Radha, Luis |  | 2019-05-06 | 2019-05-06 | Not Started
|  | Load to table (SQLite) | Luis | Brown, Krunal, Radha |  | 2019-05-06 | 2019-05-06 | Not Started
|  | Generate Dashboard | Radha | Luis, Krunal, Brown |  | 2019-05-06 | 2019-05-06 | Not Started
| 6 | Creating Database / Table | Luis |  |  | 2019-05-08 | 2019-05-15 | Not Started
| 7 | Writing Extract Program | Krunal |  |  | 2019-05-08 | 2019-05-15 | Not Started
| 8 | Writing data Cleaning & Transform Program | Radha | Brown |  | 2019-05-08 | 2019-05-08 | Not Started
| 9 | Writing Load Program | Luis |  |  | 2019-05-08 | 2019-05-15 | Not Started
| 10 | Writing Dashboard program | Radha | Luis, Krunal, Brown |  | 2019-05-08 | 2019-05-15 | Not Started
| 11 | Writing the Final Report | Radha | Luis, Krunal, Brown |  | 2019-05-15 | 2019-05-18 | Not Started